## Sheet1
Phase | Task | Start Date | End Date | Duration (Days) | Owners | Dependency | Status
1 | Internal review of requirements | 2023-10-01 | 2023-10-03 | 3 | PM | None
1 | Consultation with stakeholders | 2023-10-04 | 2023-10-07 | 4 | PM | Internal review of requirements
1 | Finalization of the requirement document | 2023-10-08 | 2023-10-12 | 5 | PM | Consultation with stakeholders
2 | Selection of technologies and frameworks | 2023-10-16 | 2023-10-19 | 4 | DTL | Finalized Requirement Document
2 | Detailed design of system modules | 2023-10-20 | 2023-10-24 | 5 | DTL | Defined Tech Stack
2 | Database design and API specification | 2023-10-25 | 2023-10-27 | 3 | DTL, DevOps Engineer | Completed Design Documents
2 | UI/UX design | 2023-10-28 | 2023-10-31 | 4 | DTC | None
3 | Backend development | 2023-11-01 | 2023-11-10 | 10 | DTL | Completed Database Design and API Specification
3 | Frontend development | 2023-11-01 | 2023-11-15 | 15 | DTL, DTC | Finalized UI/UX Designs
3 | Database setup and data modeling | 2023-11-01 | 2023-11-10 | 10 | DevOps Engineer | Completed Database Design
3 | Development of automated notification system | 2023-11-11 | 2023-11-20 | 10 | DTL | Completed Backend Development
3 | Integration of front-end with back-end services | 2023-11-21 | 2023-11-30 | 10 | DTL | Completed Frontend and Backend Development
4 | Unit and integration testing | 2023-12-01 | 2023-12-02 | 2 | QAL | Completed System Integration
4 | User acceptance testing | 2023-12-03 | 2023-12-03 | 1 | QAL | Completed Unit and Integration Testing
4 | Performance and security testing | 2023-12-04 | 2023-12-05 | 2 | QAL | Completed User Acceptance Testing
5 | Setup of production environment | 2023-12-06 | 2023-12-06 | 1 | DevOps Engineer | Completed Performance and Security Testing
5 | Deployment of application | 2023-12-07 | 2023-12-07 | 1 | DevOps Engineer | Setup of production environment
5 | Final review meeting with stakeholders | 2023-12-08 | 2023-12-08 | 1 | PM | Deployment of application
6 | Setup monitoring tools | 2023-12-09 | 2023-12-09 | 1 | DevOps Engineer | Deployment of application
6 | Provide training and support documentation | 2023-12-09 | 2023-12-09 | 1 | DTC, QAL | Deployment of application
6 | Address any post-deployment issues or bugs | 2023-12-09 | 2023-12-10 | 2 | DTC, QAL | Deployment of application
7 | Finalization of system documentation | 2023-12-10 | 2023-12-10 | 1 | DTC | Completion of all previous phases
7 | Conducting a lessons learned session | 2023-12-10 | 2023-12-10 | 1 | PM | Completion of all previous phases
7 | Project closure | 2023-12-11 | 2023-12-11 | 1 | PM | Conducting a lessons learned session